## Notes
Waterloo Wellington Wave 2 Pandemic Preparedness Plan
Notes and intentions: * Framework is adapted based on the Ontario Health West Wave 2 Action Plan * Goals and objectives are reflective of work to be initiated, underway or completed at the Regional, area, and Ontario Health Team (OHT) levels * The WW Command Triad and health system response tables provide support, a means to escalate risk, and a place to develop common vision and strategy around the COVID response * Joint planning and monitoring risk at the WW area level supports the core functions, expectations and performance of OHTs

## Wave 2 Planning Foci
CATEGORIZATION LEGEND: | Initiative Not Yet Started | Initiative Underway | Initiative Completed
Area of Focus | Current State (Wave 1) | [5 empty] | Objectives for Fall (Wave 2) | [5 empty] | Supporting Resources
| West Region | Waterloo Wellington Area | CND OHT | Guelph & Area OHT | KW4 OHT | Wellington OHT | West Region Initiatives | Waterloo Wellington Area | CND OHT | Guelph & Area OHT | KW4 OHT | Wellington OHT
Testing/ Assessment | RTAC formation with working groups in priority setting, swab allocation, assessment centres, data and lab results Opportunity to improve testing turnaround time Assessment Centre Remodelling |  | Assessment Centre Working Group meets regularly regarding move of location, staffing and coordinated cross-sector strategy. | Review of assessment center model and plan for relocation Proactive reach outs to targeted testing sites to offer support | Assessment Centre Working Group meets regularly regarding move of location, staffing and coordinated cross-sector strategy. | Assessing relocation of Mount Forest AC | Targeted, risk-informed testing campaigns, with shorter turnaround time More accessible testing (mobile units) Assessment centers stabilized with expanded capacity |  | Identifying local testing options for specialized groups (children vulnerable, isolated pts) in collaboration with PHU and identifying any gaps. Working with OHT Assessment Centre WG to be in a position to scale up testing capacity (including drive through capability and redeployment of staff to AC from primary care) as required. Assessment centre relocation | Assessment center relocated and resourced appropriately Work through OHT to reach targeted and risk-identified sites for testing | Working with OHT Assessment Centre WG to be in a position to scale up testing capacity (including drive through capability and redeployment of staff to AC from primary care) as required. Planning for increased AC capacity through new UW and drive through options | Request to add second site in RW sent to OW. Awaiting response. Utilizing community paramedicine for patients who have mobility challenges. Exploring pediatric pathway options.
IPAC | Need for IPAC to be essential function to prevent and manage outbreaks Need to build local IPAC capacity |  | IPAC Forum extended to all OHT members and affiliates. IPAC audits managed through congregate care setting support structure, primarily conducted by hospital and PHU. IPAC Team Virtual Consultations Piloted July 2019. | Identification of OHT partner organization(s) including hospital, primary care, MHA agency and/or NLOT to provide support on pandemic planning, resources, on-site coaching, outbreak support, PPE use and staffing levels | Hospitals and PHU have responded to requests for IPAC inspections; other OHT partners supporting with resources | Hospitals and PHU have responded to requests for IPAC inspections; other OHT partners supporting with resources | IPAC is embedded in all training, infrastructure and procedures in congregate settings All organizations have approved tools and resources, access to virtual or on-site community supports, and OH West IPAC functional team if required |  | Enhancing collaboration with Public Health Unit, CMH, NLOT and Public Health Ontario to offer intensive IPAC coaching locally. IPAC audits conducted by hospital and PHU. IPAC Repository to ensure quick access to evidence-based resources. | Implementation of partnered support model to optimize prevention and management of COVID outbreaks | Implementation of partnered support model to optimize prevention and management of COVID outbreaks | PH doing 2nd wave of IPAC assessments with congregate care settings in September 2020. H&CC staff have IPAC training completed. Shared OW document with physicians to utilize in their practices.
Congregate Care Settings | Proactive and reactive responses to outbreaks Sector shortage of IPAC expertise and leadership >5% beds eliminated to support IPAC (Directive 3) |  | Collaborative cross-sector congregate care support structure responds to individual needs. LTC & RH Community of Practice established and meets weekly to share lessons. | Congregate Care Setting huddles to identify and mitigate risks | Congregate Care Setting huddles to identify and mitigate risks |  | Inventory of all WW congregate care settings has Wave 2 partner teams linked and mechanism to flag and mitigate risks developed LTC/RH sector has completed preparedness planning exercise, and has identified partners Clear pathways for ALC patients |  | Collaborative cross-sector congregate care support structure extended to other congregate care settings per OH West list. OHT providing coaching support in partnership with Public Health Ontario to LTC and RHs locally re preparedness planning exercises. Engagement exercises with congregate care underway to identify improvement opportunities for Wave II response to LTC & RH. ALC working group piloting Intensive Transition Team to support ALC flow. | Implementation of partnered support model to optimize prevention and management of COVID outbreaks, including targeted support offered to homes for Wave 2 preparedness planning exercise ALC workgroup implementing strategies to improve patient flow | Implementation of partnered support model to optimize prevention and management of COVID outbreaks, including targeted support offered to homes for Wave 2 preparedness planning exercise ALC workgroup implementing strategies to improve patient flow | In process of completing preparedness assessment. Meeting Aug 20 to support LTC/RH with any questions about the assessment. Exploring opportunity to do a tabletop exercise with other congregate care settings in September 2020. Creating ALC Connectivity Table for ALC patients & at home high risk patients who are identified as at risk of hospital re-admission/visit. Continuing with our weekly huddles for congregate care settings.
Vulnerable Populations | Response strategies developed to prioritize needs of vulnerable sectors (Indigenous, Francophone, refugees, precariously housed, frail elderly) |  | Response strategies developed for vulnerable populations (homeless, frail elderly) | Response strategies developed for vulnerable populations (homeless, frail elderly, Indigenous) | Response strategies developed for vulnerable populations (homeless, frail elderly, refugees, Indigenous) | Response strategies developed for vulnerable populations (socially isolated, frail elderly) | Targeted approaches based on need Proactive models for testing |  | Enhance partnerships with PH and Sanguen Bus to ensure aligned testing processes across the OHT for vulnerable populations. | OHT partners mobilizing health hub model to support COVID and other health related needs of vulnerably housed individuals | Enhance partnerships with PH and Sanguen Bus to ensure aligned testing processes across the OHT for vulnerable populations. | LTC/RH doing staff testing on-site. One home is sending staff to the assessment centre.
Service Resumption (including capacity) | Significant closures across all sectors in Wave 2; service backlogs in home care, community health and MHA 29% decrease in primary care visits and 38% decrease of unique patients resulted in backlog of services 148k surgical procedures delayed (est. 24-81 weeks to recover) Growing occupancy pressures in acute and ICU beds; 83% increase in ED visits from April to July 2020 with increased acuity |  | Primary Care Town Hall. Service Resumption Bulletin sent to primary care to update on opening of services in the community, availability of walk-in clicnics and resumption of services in hospital. Request to maintain increased hospital capacity to MOH ALC workgroups identified patient flow issues and started to strategize around increasing capacity in hospital and in community | Request to maintain increased hospital capacity to MOH ALC workgroups identified patient flow issues and started to strategize around increasing capacity in hospital and in community | Two primary care Townhalls have been held. GRH-SMGH patient redistribution to support continued service resumption. Request to maintain increased hospital capacity to MOH ALC workgroups identified patient flow issues and started to strategize around increasing capacity in hospital and in community | Request to maintain increased hospital capacity to MOH ALC workgroups identified patient flow issues and started to strategize around increasing capacity in hospital and in community | Recovery of all sectors is actively monitored and managed to prevent increase in backlog, inequitable access to care, and/or trigger ramp-down if required Determination of core services for which access should be maintained through subsequent wave COVID-capable acute care capacity is maintained, including adoption of triggers for opening new beds and/or AHFs Procedures and surgeries are resumed and backlog is reducing, including strategies to ensure equitable access to care through regionalization of certain clinical services |  | Continue Service Resumption Bulletin to support communication. Reconsideration of triggering patient redistribution processes and initiating AHFs to support service resumption and patient flow. Identification of core services in each sector to be maintained through subsequent COVID waves. | Reconsideration of triggering patient redistribution processes and initiating AHFs to support service resumption and patient flow. Identification of core services in each sector to be maintained through subsequent COVID waves. | Reconsideration of triggering patient redistribution processes and initiating AHFs to support service resumption and patient flow. Identification of core services in each sector to be maintained through subsequent COVID waves. | Each PC setting has established process for maintaining core services; opening & closure as needed. GMCH & NWHC have "resumption of services" document. Reconsideration of triggering patient redistribution processes and initiating AHFs to support service resumption and patient flow. Identification of core services in each sector to be maintained through subsequent COVID waves. | Include sector specific recovery plans
Health Human Resources | Redeployment from partner organizations Shortage of HHR to meet health sector demand |  | Emergency Response Team trained 58 individuals for possible deployment. 3 individuals deployed, supporting 2 LTC Homes. | Redeployment of LHIN, SPO and hospital resources to support congregate care settings. | Redeployment of LHIN, SPO and hospital resources to support congregate care settings. |  | Provincial/regional pool of PSW supports available to LTC/RH sector to be deployed to meet need Providers aware of HHR resource options, including identified health system partners |  | Emergency Reponse Team re-established including identifying individuals, establishing redeployment agreements and setting out process for IPAC/OHS audits with hospital partner. Prioritization framework for staff deployment, recognizing needs in congregate care settings and Assessment Centre and emerging needs. | Proactive partnerships with congregate care settings to provide staffing resources and options. | Proactive partnerships with congregate care settings to provide staffing resources and options. | Meeting with LTC/RH Aug 20 to discuss needs & review options for planning purposes.
Supplies | Sufficient supply to meet demand but supply chain for some sectors not reliable HMMS and Ontario Health assumed allocation and distribution role |  | Support communication of how to access PPE node. | Distribution of pandemic supply PPE distribution process to appropriate sectors, while still encouraging usual procurement channels and conservation principles. | Distribution of pandemic supply PPE distribution process to appropriate sectors, while still encouraging usual procurement channels and conservation principles. | Distribution of pandemic supply PPE distribution process to appropriate sectors, while still encouraging usual procurement channels and conservation principles. | HMMS hub and spoke model maintained Reduce number of individual hubs in West Region Implementation of single swab allocation process Provincial reprocessing strategy for N95 masks Pandemic transitional PPE program implemented Domestic supply chain stabilized with centralized coordination Stability of sectors in PPE supply |  | Explore Mohawk MedBuy OHT resources to support our partners. Central reprocessing of N95 masks through Cambridge Memorial Hospital. | Monitor local and provincial stockpile supplies and source other methods of procurement. | Monitor local and provincial stockpile supplies and source other methods of procurement. | Monitor local and provincial stockpile supplies and source other methods of procurement.
Virtual and Digital Health | 73% of primary care visits occurred virtually in April- May 2020 Fee codes introduced for primary care to bill for virtual care |  | Advocacy to MOH regarding longevity of billing codes and communication to primary care regarding timeline (spring 2021). Virtual consults increased, including to specialists and ED. Adoption of Input Health and COVID contact tracing app. | Virtual consults increased, including to specialists and ED. Adoption of Input Health and COVID contact tracing app. | Virtual consults increased, including to specialists and ED. Adoption of Input Health and COVID contact tracing app. | Virtual consults increased, including to specialists and ED. Adoption of Input Health and COVID contact tracing app. | Sustain digital and virtual services Expand remote and virtual options for care |  | Communication to primary care regarding virtual care. Conduit to connect available supports and resources. Continued support for virtual care when in-person is not recommended. Explore virtual care options for individuals recovering from COVID (remote patient monitoring), and expansion of primary care access through virtual means. | Continued support for virtual care when in-person is not recommended. Explore virtual care options for individuals recovering from COVID (remote patient monitoring), and expansion of primary care access through virtual means. | Continued support for virtual care when in-person is not recommended. Explore virtual care options for individuals recovering from COVID (remote patient monitoring), and expansion of primary care access through virtual means. | Working with eHealth Centre For Excellence on options for the assessment centre. Continued support for virtual care when in-person is not recommended. Explore virtual care options for individuals recovering from COVID (remote patient monitoring), and expansion of primary care access through virtual means.

## OHT Congregate Supports
Congregate Setting Check In - August 4, 2020
| Guelph | KW4 | CND | Wellington
Huddle Type and Frequency | Meets every Thursday morning. |  | Meets every 2nd week on Wednesday mornings for 30 minutes. If required, with a plan to meet the following day at 11:00 a.m. | Meets on Wednesdays at 11:30 a.m.
Community of Practice Frequency | Meets every Wednesday afternoon. Have agreed to extend to every other week through August and return to the weekly meetings in September. | Meets every Wednesday afternoon. to discuss LTCH and RH and on Thursdays to discuss other congregate settings i.e. farms, group homes etc. | Meets every 2nd week for 30 minutes to increase uptake through August. | LTC meets twice per month in terms of COVID challenges/other issues/reporting.
IPAC Supports | IPAC sponsor have been assigned to homes. MH+A congregate settings sponsors are Homewood and CMHA. | PH follows up every Tuesday re questions, IPAC. PH inspectors followup with homes. Overall IPAC in good shape. | The check ins are done regularly by our partners - PH and MLTC currently for green homes. | Everything the same in terms of IPAC.
Approach to Green Homes | Awaiting confirmation re strategies. | A new self-assessment/reporting process is being developed by the LHIN, for Guelph, Wellington and Waterloo region | Hoping to build into a survey, similar to MHA, organized by the LHIN. | Not sure what the self-assessment will look-like at this stage.
Human Resources
Sustained Operations
Pandemic Plan